In-Class Activity

### Risk Response Planning

#### Shopify Inc. - Vantage Discovery Acquisition

| Student | NUID |
| --- | --- |
| Terry Lucas Boye | 002595573 |
| Lissette Diaz | 003163767 |
| Ekene Onyemanjo | 002336956 |

Northeastern University

College of Professional Studies

Course: ALY 6130 – Risk Management

Instructor: Abeba Nigussie Turi

Date: June 19th, 2026

### Risk 1: Loss of Merchants to Amazon/Google AI Search Competition (T1 Negative)

Heat Map Position: High Probability × High Impact | Monte Carlo: 100% L1 breach | P50 loss: $133.8M

Response Strategy: Mitigation/Reduction

Justification: Avoidance is not feasible; Shopify cannot exit the AI search market after acquiring Vantage Discovery without abandoning its core strategic investment. Transfer is also impractical because merchant churn risk cannot be insured or contractually shifted to a third party. Acceptance would be irresponsible given the 100% L1 breach probability confirmed by the Monte Carlo simulation. Mitigation is therefore the only appropriate strategy; the goal is to reduce both the likelihood of merchant churn and its financial impact through proactive retention and product quality controls.

Response Plan:

- Phased rollout with performance gates: Deploy Vantage Discovery AI search to a controlled beta cohort of Shopify merchants before full platform release. Establish a minimum acceptable search relevance score before advancing to the next deployment phase.

- Legacy search fallback system: Maintain the existing Shopify search infrastructure in parallel during integration.

- Shopify Plus retention program: Given that Plus merchants contribute disproportionately to ARR, deploy a dedicated white-glove retention team for the highest-value merchant segment.

- Competitive benchmarking dashboard: Establish a monthly internal benchmark comparing Vantage Discovery's search relevance and conversion lift against Amazon and Google Shopping AI.

- KRI monitoring: Merchant Churn Rate monitored weekly. Amber threshold: >2% monthly. Red threshold: >4% monthly OR >1.5% among Shopify Plus merchants triggers emergency retention protocol and CTO escalation.

### Risk 2: Regulatory Non-Compliance with PIPEDA / EU AI Act / CCPA (T3 Negative)

Heat Map Position: Moderate Probability × Maximum Impact | P50 fine: $128.2M | Tail risk: $508M

Response Strategy: Mitigation/Reduction + Transfer (hybrid)

Justification: Avoidance would require Shopify to not deploy LLM-based AI features at all, which contradicts the entire purpose of the Vantage Discovery acquisition. Full acceptance is ruled out given the catastrophic tail risk of $508M. The hybrid approach combines mitigation reducing the likelihood of non-compliance through governance controls with partial transfer through regulatory liability insurance and legal indemnification clauses in vendor contracts, reducing the financial impact if a breach does occur.

Response Plan:

- Pre-launch AI compliance audit: Before Vantage Discovery AI search is deployed to any live merchant storefront, commission an independent third-party audit assessing compliance with GDPR, PIPEDA, CCPA, and the EU AI Act's high-risk AI system classification requirements. No deployment proceeds without audit sign-off.

- AI Governance Officer appointment: Hire or designate a dedicated AI Governance Officer responsible for LLM transparency documentation, algorithmic bias review, and ongoing regulatory horizon scanning across all jurisdictions where Shopify operates.

- Data minimization and purpose-limitation policy: Implement strict controls on what consumer behavioral data is ingested by the Vantage Discovery LLM, ensuring only data necessary for search personalization is processed.

- Jurisdiction-specific data residency: Establish separate data residency environments for EU and Canadian user data, ensuring that cross-border data transfers comply with GDPR Chapter V restrictions and Canada's evolving AIDA framework.

- Regulatory liability insurance (Transfer element): Obtain cyber and regulatory liability insurance covering first-party regulatory investigation costs and third-party fine exposure up to a defined policy limit. This does not eliminate the risk but caps the worst-case financial consequence below the $508M tail scenario.

- KRI monitoring: Number of high/critical severity regulatory findings unresolved beyond 30 days. Amber: 1–2 findings. Red: ≥3 findings OR any confirmed regulatory investigation triggers immediate board-level escalation and legal counsel engagement.

### Risk 3: New Merchant Segment Expansion via Contextual AI Search (O1+O3 - Positive)

Heat Map Position: Moderate Probability × High Positive Impact | Monte Carlo: 45.1% probability of exceeding L1 | P50: $491.3M ARR upside

Response Strategy: Exploit/Enhance (Positive Risk)

Justification: Because this is a positive risk an opportunity rather than a threat, the appropriate PMBOK/COSO response strategies shift from avoidance and mitigation to exploitation and enhancement. Exploitation aims to ensure the opportunity is fully captured; enhancement aims to increase its probability and/or impact. Given that the 6 to 18 month competitive window is time-limited and that competing platforms are actively developing equivalent AI features, a passive acceptance approach would forfeit a $491.3M P50 ARR opportunity. Immediate, resource-backed action is required.

Response Plan:

- Targeted competitor migration campaign: Launch a dedicated acquisition campaign within 30 days of Vantage Discovery AI search going live, specifically targeting merchants on Amazon Seller Central, Wix, and BigCommerce who have publicly expressed platform dissatisfaction.

- Time-limited migration incentives: Offer waived platform fees for the first three months and free onboarding support to merchants migrating from a competing platform during the first 12 months of the campaign window.

- Proactive onboarding capacity scaling: Pre-authorize hiring of additional merchant onboarding specialists before the campaign launches, not after volume increases.

- AI search case study content: Develop and publish merchant success stories demonstrating measurable conversion rate improvements from Vantage Discovery's contextual AI search, targeting the SMB and mid-market segments most likely to migrate.

- KRI monitoring: Net New Merchant Acquisition Rate from competing platforms. Amber: 5–15% above baseline activates campaign scaling. Red: >15% above baseline escalates to COO for onboarding capacity authorization. This Red threshold signals a positive risk breach requiring resource deployment, not a threat response.

### Summary Table

| Risk | Strategy | Primary Rationale | Key Action |
| --- | --- | --- | --- |
| R-001 AI Competition | Mitigation | Cannot avoid or transfer; 100% L1 breach demands active reduction | Phased rollout + Plus retention program |
| R-002 Regulatory | Mitigation + Transfer | Hybrid reduces probability and caps tail financial impact | Pre-launch audit + liability insurance |
| R-003 Market Expansion | Exploit + Enhance | Time-limited positive risk; passive acceptance forfeits $491.3M P50 | Immediate migration campaign launch |

#### References

BetaKit. (2025). Shopify acquires Vantage Discovery. https://betakit.com

COSO. (2017). Enterprise risk management: Integrating with strategy and performance. COSO.

Hopkin, P. (2018). Fundamentals of risk management (4th ed.). Kogan Page.

Recurly. (2024). Subscription benchmarking report. https://recurly.com

Shopify Inc. (2026). Q1 2026 earnings press release [Form 8-K]. SEC EDGAR. https://www.sec.gov

Turi, A. N. (2026). ALY 6130 course materials. Northeastern University.