## Sheet1
Risk # | Date | The Risk of/That | Caused by | Resulting In | Consequence/Impact | Likelihood Score | Impact Score | Risk Score | Priority (H, M, L) | Mitigation | Risk Owner | Open/Closed
1 | June 1, 2026 | Loss of active merchants to competitors with more established AI search capabilities. | Potencially slow or incomplete integration of Vantage Discovery into Shopify's platform. | Migration of merchants away from Shopify's platform toward competitors with already-integrated AI search solutions. | Financial: Revenue loss due to reduced merchant activity and online sales. Operational: Increased workload and resource strain on the integration team, potentially delaying timelines. Reputational: Shopify is perceived as lacking the capacity to successfully execute this integration. | 3 | 4 | 12 | H | 1. Conduct an internal audit prior to integration to assess the pre-integration landscape. 2. Implement a phased integration approach. 3. Establish a continuous monitoring process. | Chief Technology Officer / Integration Team | Open
2 | June 1, 2026 | Regulatory non-compliance with PIPEDA, the EU AI Act, and other emerging AI regulations due to the integration of LLM-based search technology. | Shopify's use of Large Language Models (LLMs) and customer behavioral data through Vantage Discovery may create privacy, transparency, consent, and algorithmic governance challenges across multiple jurisdictions. | Regulatory investigations, compliance findings, legal actions, operational disruption, and increased compliance costs associated with remediation activities. | Financial: Regulatory fines, legal expenses, and increased compliance costs. Strategic: Reduced merchant and customer trust in Shopify's AI capabilities. Operational: Delays in AI deployment due to corrective actions and regulatory reviews. Reputational: Negative publicity resulting from privacy or AI governance violations. | 3 | 5 | 15 | High | 1. Establish an AI Governance Committee responsible for oversight of all AI-enabled solutions. 2. Conduct quarterly privacy impact assessments and AI compliance reviews. 3. Implement data minimization, consent management, and model transparency controls. 4. Maintain legal monitoring of emerging regulations including PIPEDA, AIDA, GDPR, and the EU AI Act. 5. Monitor KRI: High-Severity Regulatory Compliance Findings per Quarter. Green = 0 findings; Amber = 1 finding; Red = 2+ findings or any formal regulatory investigation. | Chief Compliance Officer / Legal & Compliance Team | Open
3 | June 1, 2026 | Accelerated expansion into new merchant segments through contextual AI search, driven by growing demand for AI-powered commerce tools and Shopify's open platform ecosystem advantage | Rising merchant demand for personalized, context-aware AI search capabilities (O1: increased sales growth driven by AI and agentic commerce) combined with Shopify's open and flexible platform model attracting merchants seeking independence from restrictive larger ecosystems such as Amazon Marketplace (O3), with Vantage Discovery's LLM technology providing a differentiated capability that smaller competitors cannot yet replicate | Accelerated net new merchant acquisition across SMB and mid-market e-commerce segments, increased average revenue per merchant through AI-driven upsell opportunities, and strengthened network effects from a larger and more diverse merchant base, amplifying the long-term return on the Vantage Discovery acquisition investment | Financial: Incremental ARR growth of 3–6% if new merchant segment opportunity is actively captured during the integration window. Strategic: Permanent market share gains with strong AI-feature switching-cost lock-in, reducing future churn risk once merchants build workflows around Shopify's contextual search capabilities. Operational: Onboarding resource strain if merchant acquisition volume exceeds current support infrastructure capacity, requiring proactive scaling. Brand: Successful AI-driven merchant growth reinforces Shopify's positioning as the leading AI-first commerce platform (BetaKit, 2025). | 3 | 4 | 12 | High | 1. Launch dedicated AI-powered merchant acquisition campaign targeting merchants on restrictive platforms (Amazon Seller Central, Wix). 2. Develop contextual AI search case studies to demonstrate ROI to prospective merchants. 3. Offer time-limited migration incentives (waived fees, extended trials) to capture window. 4. Scale onboarding team capacity proactively before campaign launch to avoid service degradation during volume surges. 5. Monitor KRI: Net new merchant acquisition rate from competing platforms: Green < 5% above baseline; Amber 5–15% (activate campaign scaling); Red > 15% (onboarding capacity stress, escalate to COO). | Chief Revenue Officer / Growth Marketing Team | Open